## Plan
No. | Tasks |  |  | In-charge | [40 empty] | 2020
[6 empty] | Apr. |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar. |  |  |  |  | Apr. |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[6 empty] | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
1 | CSI OT Platform Enhancement Phase II |  |  | Pete, JunWen, YuanCheng, Shantanu
| 1.1 | Hand-over of Phase I attack Scenarios to CSI |  | Pete, JunWen, CSI
|  | 1.1.1 | Fault-Data Inject Attack Scenario | bar: Jan 13
|  | 1.1.2 | Black-out Attack Scenario | bar: Jan 13
| 1.2 | New Assets additional to CSI OT Platform |  | by Vendor | bar: Jan 13 to Mar. 23
|  | 1.2.1 | Power-Grid model
|  | 1.2.2 | Input pump & generator
|  | 1.2.3 | Power i/p & o/p LED Display
|  | 1.2.4 | Power Processing System
|  | 1.2.5 | Alert / Buzzer System
|  | 1.2.6 | Additional Processing Platform
|  | 1.2.7 | Add the power plan model auto control device & program (new Raspi) | Yuancheng | bar: May 4 to Aug 10
| 1.3 | Enhancement of CSI OT Platform with new Attack Scenarios |  | JunWen, YuanCheng, Shantanu
|  | 1.3.1 | Enhancement to Fault-Data Inject Attack Scenario | Shantanu
description?
|  | 1.3.2 | Enhancement to Black-out Attack Scenario | Shantanu
description?
|  | 1.3.3 | Additional Stealthy attack | Shantanu
description?
| 1.4 | Defend mechanism for Stealthy attack |  | Shantanu, JunWen
|  | 1.4.1 | Design and planning | bar: Jul 6 to Jul 27
|  | 1.4.2 | Implementation | bar: Aug 3 to Sep 28
|  | 1.4.3 | Feedback and enchancement | bar: Oct 5 to Dec 28
| 1.5 | Web Portal
|  | 1.5.1 | Integrate old attack web-portal with new | YuanCheng | bar: Jul 20 to Aug 10
|  | 1.5.2 | Add the attack states display and feed back in the new attack control page which same as the old one. | YuanCheng | bar: Jul 20 to Aug 24
| 1.6 | Upgrade HMI with new Assets
|  | 1.6.1 | Adding "Power-Grid" control to the trainer UI/recapture the pphoto | YuanCheng | bar: Jul 20 to Sep 7
|  | 1.6.2 | Add the Power Generator Model state display section in the HMI. | YuanCheng | YuanCheng | bar: Jul 20 to Aug 17
|  | 1.6.3 | Integrate old ladder diagram with "Power-Grid" ladder diagram | bar: Aug 24 to Sep 28
|  | 1.6.4 | Integrate and test all the different attacks
|  | 1.6.5 | Operational HMI for the Power Grid
description?
|  | 1.6.6 | Diagnostic HMI (optional)?
| 1.7 | Using OT platform for OT class training
|  | 1.7.1 | Using CSI OT platform to illustrate attacks taught in the class | Shantanu, Pete
2 | CSI OT Class
| 2.1 | CSI OT Platform Enhancement by Prof. Biplab |  | Prof. Biplab, Pete & JunWen
| 2.2 | Enhancement of CSI OT 3-days Training material |  | Prof. Biplab | bar: May 4 to May 25
First Draft of slides
Feedback from CSI | bar: Jun 1 to Jun 15
Revision | bar: Jun 22 to Jun 29
Finalization
| 2.3 | Trial class with CSI / Topics for marketing |  | Prof. Biplab / CSI | bar: Jul 6 to Jul 27
| 2.4 | Enhancement of 3D OT platform, attack scenario + description |  | Dr. Shantanu
Schematics of 3D platform | bar: Jul 6 to Jul 13
Development and implementation of experiment idea - AGC (new asset) | bar: Jul 20 to Aug 17
Development of experiment idea - Defence against new attacks | bar: Aug 24 to Sep 28
Feedback from CSI | bar: Oct 5
Modifications to idea | bar: Oct 12
Implementation (with planning for future defence strategies) | bar: Oct 19 to Dec 28
|  | Proposal for conducting the class? |  | Prof. Biplab & Shantanu